ALLTECH AV Marketing & Growth Coordinator · Level ? · EOS-Aligned 90-Day Onboarding Plan [Name] · Start: [Date] Managed by Elena Melnykova - Director of Operations & Marketing

Purpose of This Plan This is not a task checklist. It is a structured progression of responsibility, context, and ownership - designed to bring you from your first day to full, independent execution across all 6 marketing pillars. Month 1 (Jul): Immerse & Audit · Month 2 (Aug): Build Foundations · Month 3 (Sep): Execute & Own No live content posts until October - Month 1 and 2 are about building the foundations properly so everything that goes out is right from day one.

| ✅ Operational Outcomes Content calendar live and posts queued. 10 case studies published. Website redesign proposal delivered. HubSpot essentials running. First sales asset delivered. All SOPs documented. | ✅ Behavioural Outcomes(Growth Tracker Level 4→5) Own your work without supervision. Communicates proactively. Thinks commercially - not just creatively. Produces output that Seb is proud to put in front of clients. | ✅ Strategic Outcomes You understand Alltech's business, clients, market, and competitive landscape deeply enough that by Month 3 she is contributing ideas - not just executing instructions. |
| --- | --- | --- |

🚀 PRE-START - Before You Arrive Week of 30 June 2026 · Elena's responsibility to have all of this ready before Day 1

Admin & System Access (Elena to complete)

- Create Alltech email address (e.g. name@alltech.co)

- Set up email signature - Name, Role, Phone, Website

- Add to Google Workspace with correct Drive folder permissions

- Add to shared Google Calendar + all team calendars (including Seb's)

- Set up in Teamwork - workspace created, Month 1 tasks assigned before Day 1

- Add to any channels or internal communication tools in use

- Confirm physical workspace arrangement for on-site days

Brand & Content Access (Elena to prepare)

- Brand assets folder ready: logos (all versions), colour palette, fonts, existing templates

- Past project folder - curated shortlist of 30+ best jobs from last 5 years with photos and any existing descriptions

- Access to all existing social media accounts (LinkedIn, Instagram, any others) with login credentials

- Website CMS login credentials

- Any past marketing materials (booklets, decks, one-pagers) - even rough ones, so you understand what has previously existed

- Client list overview - industry breakdown, top 10–15 clients by value and relationship

Culture & Team Prep

- Email you the week before: what to expect on Day 1, who you’ll meet, what to bring, any reading to do in advance (link to Role Blueprint)

- Request one personal photo from you (childhood photo preferred, with a short story - team intro tradition)

- Draft team intro email (from Seb or Elena) - ready to send on Day 1 morning

- Book Day 1 schedule: Elena (morning full immersion), Seb (30 min), staggered team intros throughout the day

- Brief the team on your arrival: who you are, what your role is, and how to work with you

🔵 MONTH 1: IMMERSE & AUDIT 7 July – 1 August 2026 · 24 hrs/week Goal: Build deep understanding of Alltech's brand, business, team, and current marketing state. No live content this month - audit and foundation only.

🔥 Week 1 - Full Business Immersion (7–11 July)

Week 1 is about listening, watching, and absorbing. You should finish Week 1 able to describe Alltech's work, team, and clients as if  you’ve been here for months.

Business & Team Immersion

- Day 1 (morning): Full Alltech walkthrough with Elena - what the business does, how jobs flow from quote to delivery, who the key clients are, what the brand should feel like

- Day 1: Physical warehouse tour with Josh - understand the equipment, the scale, and what 'a well-run AV job' looks like physically

- Day 1: Meet Seb (30 min) - understand his vision for the brand, what excites him about marketing, and what 'good' looks like in his mind

- Week 1: Individual intros with Adam, Josh, and Marley - understand each role, how they experience Alltech, and what marketing could do for them

- Review all existing Google Drive structure - understand where everything lives before touching anything

- Review past project photos and any existing case study materials - build a feel for the portfolio

EOS & Systems Introduction (Week 1)

- EOS introduction with Elena: what EOS is, how Level 10 meetings work, how the scorecard operates, and your place in the cadence

- Review your final Role Blueprint and Growth Tracker with Elena - set expectations clearly from Day 1

- Teamwork induction: how the team uses it, how you will manage your own workflow and tasks

- Google Calendar: confirm access to all calendars and understand the company rhythm (jobs, meetings, events)

- Google Drive Mapping & Permissions familiarisation

- HubSpot: orientation only - understand the current state before building anything

🔥 Weeks 1–2 - Brand, Social Media & Website Audits (7–18 July)

These three audits are Month 1's core deliverables. Each results in a written report presented to Elena.

Social Media Audit - Due: End of Week 2

- Pull all historical performance data from every existing channel (LinkedIn, Instagram, Facebook, any others)

- Analyse: what content was posted, when, in what format, what performed, what didn't, what tone was used

- Competitive benchmark: review 3–5 direct competitors' social presence - what channels, what content, what engagement

- Platform recommendations: which channels should Alltech prioritise and why

- Output: Social Media Audit Report in Google Drive - presented to Elena end of Week 2, and used to inform the Month 1 strategy session

Website Audit - Due: End of Week 2

- Full UX review: navigation, site structure, mobile responsiveness, page load speed

- Content review: is the messaging accurate, current, and compelling? Does it reflect who Alltech is today?

- SEO baseline: current keyword visibility, meta data status, site health, and technical SEO gaps

- Conversion review: what is the site asking visitors to do? Is there a clear path to contact? Does it work?

- Competitor comparison: how does alltechav.com.au compare visually and editorially to 3 competitors?

- Output: Website Audit Report in Google Drive - presented to Elena end of Week 2

Brand & Asset Audit - Due: End of Week 2

- Review all existing brand assets: logos, colour palette, fonts, templates, printed materials, digital graphics

- Identify what exists, what's inconsistent, what's missing, and what needs to be rebuilt from scratch

- Review any past marketing materials - assess quality, brand alignment, and whether they're still usable

- Output: Brand Asset Inventory in Google Drive - simple table format, actionable

🔥 Weeks 2–3 - Marketing Strategy Session (14–18 July)

Marketing Strategy Session with Elena

- Elena leads; You prepare by bringing audit findings and researched recommendations

- Session agenda: channel strategy, content pillars and formats, brand voice and visual direction, 3/6/12-month priorities

- You document all decisions and builds the agreed marketing plan in Google Drive

- Output: 3-month, 6-month, and 12-month marketing plan drafted - to be reviewed and signed off by Seb

- This session determines: which channels, what content types, what posting frequency targets, and what the priority output order is

🔥 Weeks 2–4 - Case Study Foundation (14 July – 1 Aug)

Case Study Framework Setup

- Build the case study tracker (Google Drive or Excel): project name, industry, event type, scale, visual assets available, PM/contact, priority, status

- Review past project list with Elena and Seb - identify the 20 most suitable projects, prioritised by visual impact and commercial relevance

- Develop the case study template: Client Brief / Challenge / Solution / Outcome / Visuals

- Interview at least 2 team members (PM or Seb) for the first 2 case studies - practice and refine the extraction process

- Write and format the first 3 case studies - presented to Elena for review before end of Month 1

- Document the interview and writing process as an SOP before the end of Month 1

🔥 Weeks 3–4 - HubSpot & Sales Enablement Planning (21 July – 1 Aug)

HubSpot - Month 1 Scope (Setup Only)

- Orientation: understand the full current HubSpot setup - what exists, what's been configured, what hasn't

- Map the sales pipeline structure needed: deal stages, for which users (Seb, Junior PM, Admin, Elena), and what data each user needs

- Plan email sequence and automation structure with Elena - what triggers what, for whom, and when

- Month 1 deliverable: a HubSpot setup plan (timeline, responsibilities, milestone chart) documented and presented to Elena

- Do not build or launch anything in Month 1 - map and plan only

Sales Enablement Suite - Scoped in Month 1

- Review all Alltech services and identify the full suite of materials needed: service booklets, pitch deck, capability statement, video content, one-pagers

- Build a prioritised Sales Enablement Scope document - a clear list with audience, format, priority ranking, and estimated effort for each asset

- Present to Elena by end of Month 1 - this becomes the production roadmap for Months 2–6

Month 1 Scorecard

| Competency | Expected Position | Red Flag (Needs Attention) |
| --- | --- | --- |
| Output & results | Yellow - no live content yet; audit reports, case study drafts, and plans delivered to Elena | No audit documents delivered by end of Month 1 / no case study drafts started |
| Initiative | Green - asking questions, identifying gaps, bringing ideas from audit findings proactively | Waiting to be told what to do every day; no self-directed work |
| Communication | Green - weekly structured updates to Elena; no surprises; flags blockers early | Seb or others receiving direct marketing requests from you without going through Elena |
| Attention to detail | Green - audit reports are thorough, researched, and clearly presented | Audits are surface-level, vague, or not backed by data |
| Cultural integration | Green - building genuine relationships with the full team; knows who everyone is and what they do | Isolation; reluctance to engage team; no relationship with Adam, Josh, or Marley |

🟡 MONTH 2: BUILD FOUNDATIONS 3 August – 29 August 2026 · 24 hrs/week Goal: Build the systems, processes, and content foundations that everything else runs on. Still no live posts - quality foundations before launch.

🔥 Content Process & Calendar - Foundation Built This Month

No posts go live in August. The entire month is about building the system so that when content does go live in October, it's already running properly.

Content Process Development - Due: 10 August

- Document the full social media content process as an SOP: brief → draft → design → copy → approval (Elena) → schedule → report

- Document the case study content process as an SOP: project identification → interview → draft → Elena review → design → publish

- Determine the tech stack: what tool manages the content calendar (Google Drive, HubSpot, or other - present recommendation to Elena)

- Map out dedicated hours per week for each content type at 24 hrs/week - ensure the workload is realistic and sustainable

- All process documents stored in Google Drive - structured, searchable, and accessible to Elena and Seb

Content Calendar - Due: End of August

- Build the master content calendar in the agreed tool - structured by channel, week, content type, and status

- October content calendar: fully built, content gathered, captions written, graphics designed or briefed, posts queued and ready

- November content calendar: same - fully ready before you move to execution in October

- All content in the October and November calendars requires Elena's review and approval before queuing

- Elena + Seb 10-minute monthly content review: first review in August/September for October's content - this is a recurring monthly meeting

🔥 Case Studies - 5 Completed and Ready to Publish

- Complete and format 5 case studies using the agreed template (developed in Month 1)

- All 5 reviewed by Elena before publication

- Schedule the 5 case studies to publish in September as part of the content calendar

- Build the PDF portfolio template - one master Canva or InDesign file that can be updated as cases are added

- Identify the next 5 case studies and begin extraction interviews - second batch ready to publish by end of September

🔥 HubSpot - Essentials Setup Begins

- Build the sales pipeline: deal stages configured for Seb, Junior PM, Admin, and Elena - each user can see and action their deals

- Build email templates: first touchpoint, follow-up sequence, and newsletter framework

- Configure contact and company record properties - standardised fields agreed with Elena

- Task setup: how tasks are assigned, what the naming convention is, and how reminders work

- HubSpot essentials target: live and in basic use by end of August

- Full automation, sequences, and Rentman integration to follow in September–October

🔥 Website Redesign - Proposal Delivered

- Build the full redesign proposal document: recommended platform (if change needed), proposed site structure and page list, content hierarchy, UX approach, timeline, budget estimate, and any additional resource needs (e.g. web developer)

- Present to Elena (and Seb if needed) by end of August - approval needed before redesign work begins in September

- Begin copywriting for key pages in parallel (Home, About, Services, Contact) - so copy is ready when build begins

- All copy reviewed and approved by Elena before any building starts

🔥 Sales Enablement - First Booklet Underway

- Using the scoped list from Month 1, begin work on the first priority service booklet

- You write the copy; Elena reviews; Seb approves key positioning statements before design begins

- Design in Canva (or equivalent) - professional, on-brand, print-ready format

- Target: booklet in final review with Elena and Seb by end of Month 3 (September) / delivered by end of October

Month 2 Scorecard

| Competency | Expected Position | Red Flag (Needs Attention) |
| --- | --- | --- |
| Output & results | Yellow → Green - 5 case studies done, HubSpot essentials live, content calendar built | Nothing built by end of Month 2 / still no concrete outputs |
| Process & systems | Green - content SOP, case study SOP, and content calendar framework all documented | Working without documented processes; nothing in Google Drive |
| Execution quality | Green - case studies are professional, on-brand, and factually accurate | Content that looks off-brand, contains errors, or misrepresents client work |
| Communication | Green - weekly updates, Elena content review booked and running, no surprises | Elena finding out about problems after the fact |
| HubSpot progress | Green - essentials live and in basic use; full build plan clear and on track | No HubSpot progress by end of Month 2 |

🔴 MONTH 3: EXECUTE & OWN 1 September – 30 September 2026 · 24 hrs/week Goal: First case studies go live. HubSpot builds out. Website redesign begins. You demonstrates 75% independent operation.

Month 3 is the trust benchmark. By the end of September, Elena should be stepping back from day-to-day management and into pure strategic direction - confident that you have this.

🔥 Case Studies - Published

- First 5 case studies published: live on website, added to PDF sales enablement library, and queued in the social media calendar - target 4 September

- Second 5 case studies: developed during September, published by end of September (10 total live)

- Case study publication process running smoothly: You manage the pipeline of projects, interviews, drafts, and Elena reviews independently

🔥 HubSpot - Full Build Continues

- Email automations: lead nurturing sequences, follow-up workflows, and newsletter framework built and tested

- Rentman integration: define the integration requirements (data fields, sync direction, triggers) and present a clear integration plan to Elena

- Team training in September–October: all 4 users (Seb, Junior PM, Admin, Elena) onboarded and using HubSpot actively

- Troubleshoot and resolve any setup issues - work through tickets, edge cases, and user friction

🔥 Website Redesign - Begins

- Following Elena's approval of the August redesign proposal, redesign work begins in September

- Elena approves all structural decisions, page hierarchy, and copy before anything is built

- Work through pages systematically - Home and Services first as the highest-impact pages

- Website redesign target: live by 2027 (exact date confirmed in the proposal - this is a quality-first, not speed-first, project)

🔥 Social Media - Content Queued, Launching October

- October and November calendars fully built, reviewed by Elena (and Seb in the monthly content review), and approved

- Posts queued in the scheduling tool - ready to launch from 1 October

- No live posts yet in September - the queue must be fully approved before launch

- You prepare the first monthly performance reporting template - ready for use from October

🔥 SOP Library - Completed This Month

- Social media content process SOP - finalised and in Google Drive

- Case study process SOP - finalised and in Google Drive (including interview questions, template, publication checklist)

- Website update process SOP - how content requests are received, reviewed, and published

- HubSpot data hygiene SOP - contact management, deal updates, data cleanliness standards

- Content capture workflow SOP - how job site and event content is requested, captured, edited, and published

- All SOPs reviewed by Elena and stored in the Marketing section of Google Drive

🔥 Partnerships - Outreach Initiated

- Women in AV Australia: first formal outreach made - whether an email, LinkedIn message, or direct contact at an event

- You prepare the outreach brief and Elena signs off before any contact is made

- Begin building a simple partnership tracker: organisation, contact, relationship status, next action

🔥 3-Month Marketing Review with Elena

- End of Month 3: structured review session with Elena - what was planned vs. what was delivered, what worked, what didn't, and what adjusts for Months 4–6

- You prepare the review document - this is a formal EOS-style rocks and results review

- Output: updated 6-month plan with any adjustments needed based on Month 3 learnings

Core Benchmark: 75% Independence Across All 6 Pillars

| Pillar | The Trust Question Elena Asks at End of Month 3 |
| --- | --- |
| Content & Social | Are October and November content calendars fully built, approved, and queued - with posts ready to launch - without Elena having to prompt? |
| Case Studies | Are 10 case studies published? Is the interview and writing process running on its own - PMs know to brief you after significant jobs? |
| Website | Is the redesign underway following an approved proposal? Are you driving it forward, flagging blockers, and coming to Elena with decisions? |
| HubSpot | Are automations being built, team training underway, and Rentman integration scoped - with Elena informed but not doing any of it? |
| Sales Assets | Is the first service booklet in final review? Is the full suite production roadmap being followed month by month? |
| Research & Growth | Has Women in AV outreach been made? Are you surfacing research and growth opportunities proactively - not just completing assigned tasks? |

Month 3 Scorecard - Graduation Benchmark

| Competency | Target by End of Month 3 | Stretch - High Green |
| --- | --- | --- |
| Ownership | Green - all 6 pillars moving without chasing | High Green - pre-empting blockers before they surface |
| Execution quality | Green - professional, commercially sharp, on-brand | High Green - Seb comments positively without prompting |
| Process discipline | Green - all SOPs documented; Notion is the source of truth | High Green - You review and improve your own processes |
| Strategic contribution | Yellow → Green - contributing ideas, not just executing tasks | Green - raising opportunities Elena hasn't thought of |
| Cross-team integration | Green - team knows you, trusts you, sends you content ideas | High Green - Adam or Josh proactively flag content opportunities |
| Communication & reporting | Green - weekly rhythm locked in; structured review completed | High Green - You anticipate Elena's questions before they're asked |

🔵 MONTHS 3–6: SCALE · October – December 2026 Goal: Full rhythm across all 6 pillars. Marketing engine running independently. Seb's confidence in Alltech's brand presence is high.

| Focus Area | What Full Ownership Looks Like | Target Milestone |
| --- | --- | --- |
| Social media live | Posts going live from 1 October - 2–3/week across agreed channels. You manage end-to-end: brief, create, schedule, report monthly. Content feels unmistakably Alltech. | From 1 Oct |
| Case study library | 20+ published case studies by end of December. Every significant job gets a case study. PDF library and website library both current and used actively in sales conversations. | 20+ by Dec |
| HubSpot fully live | All 4 users active. Automations and sequences running. Rentman integration live. Reporting dashboards active. Seb using HubSpot daily without prompting. Including Newsletter. | Nov |
| Website redesign | Redesign underway. All pages drafted and in review. Analytics and SEO tracking in place. Launch target 2027. | Ongoing → 2027 |
| Sales enablement suite | Full suite complete: all service booklets, pitch deck, capability statements. Reviewed, approved, in Seb's hands and in the sales library. | By Dec |
| Video / podcast | Concept developed, format agreed, first piece produced or fully scheduled for production. | Dec |
| 3–5 year roadmap | Big picture marketing plan drafted with Elena, presented to Seb, approved and referenced in Q4 quarterly planning. | End Oct |
| Partnerships | Women in AV relationship in active nurturing. At least 1 additional partnership opportunity researched and presented to Elena. | Dec |
| Monthly content review | Elena + Seb 10-min monthly content review running consistently. You are preparing the agenda. Approval rhythm is smooth. | Oct–Dec |
| Q4 strategic review | Full 6-month review with Elena and Seb. Role assessed for hour expansion (28–30 hrs/week). 2027 marketing roadmap kick-started. | Dec |

Final Note This onboarding is not about completing tasks - it is about you becoming the person who owns Alltech's marketing voice, builds its brand presence, and enables its sales engine. Success means: Alltech's marketing runs consistently, commercially, and confidently - with or without Elena's day-to-day involvement. The best marketing function is one that doesn't stop when Elena is in Thailand.